## Outputs
Documentation/Output | Phases | Phase 0 Readiness | Phase 1 Readiness | Phase 2 Selection | Phase 3 Engagement | Phase 4 Migration | Phase 5 Operations
Vision Statement | 0 | Version 1
In-scope service area(s) and function(s) | 0 | Version 1
Expected Benefits | 0 | Version 1
High Level Timelines | 0 | Version 1
Major IT Business Case | 0 | Version 1
Program Charter | 1, 3 |  | Version 1 |  | Updated
HR/Staffing Plan | 1,2,3 |  | Version 1 | Updated | Updated
Program Management Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Initial Master Schedule | 1,2 |  | Version 1 | Updated
Independent Verification & Validation (IV&V) Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Status Reports/Dashboards | 1,2,3 |  | Version 1 | Updated | Updated
Governance Charter | 1,3 |  | Version 1 |  | Updated
Risk Management Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Risks, Actions, Issues, and Decisions (RAID) Log | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
M3 Risk Assessment | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Procurement Plan | 1,2,3 |  | Version 1 | Updated | Updated
Quality Assurance Surveillance Plan (QASP) | 1 |  | Version 1
Life Cycle Cost Estimate (LCCE) | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Baseline Performance and Success Metrics | 1 |  | Version 1
Target Performance and Success Metrics | 1 |  | Version 1
Stakeholder Analysis | 1 |  | Version 1
Communications Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Migration and Operations and Maintenance (O&M) training needs | 1 |  | Version 1
As-Is Workforce Documentation | 1 |  | Version 1
Change Readiness Assessment | 1 |  | Version 1
As-Is Systems Environment | 1 |  | Version 1
Target State Systems Environment | 1,3 |  | Version 1 |  | Updated
Data Governance Model | 1 |  | Version 1
Data Cleansing Plan | 1,2,3 |  | Version 1 | Updated | Updated
Target State Concept of Operations | 1,3 |  | Version 1 |  | Updated
Scope of Services updated in the Business Needs Workbook | 1 |  | Version 1
Requirements Management Plan | 1,3 |  | Version 1 |  | Updated
Business Needs Workbook | 1,2 |  | Version 1 | Updated
Business Capabilities | 1 |  | Version 1
Evaluation Criteria | 2 |  |  | Version 1
Draft Request for Information (RFI) and Responses (Commercial Only) | 2 |  |  | Version 1
Implementation Approach/Schedule | 2 |  |  | Version 1
Price Estimates for Engagement, Migration, and O&M | 2 |  |  | Version 1
Provider Assessment Report (Federal Only) | 2 |  |  | Version 1
Engagement Phase Interagency Agreement (IAA) (Federal Only) | 2 |  |  | Version 1
Draft Request for Proposal (RFP) (Commercial Only) | 2 |  |  | Version 1
Labor Relations Strategy | 2,3,4 |  |  | Version 1 | Updated | Updated
Change Management Plan | 2,3,4 |  |  | Version 1 | Updated | Updated
Baseline Readiness Assessment | 2 |  |  | Version 1
Data Cleansing Scripts | 1 |  |  | Version 1 | Updated
Decommission Plan | 2,3,4 |  |  | Version 1 | Updated | Updated
Business Process Reengineering Strategy | 2,4 |  |  | Version 1 |  | Updated
Validated As-Is Process Maps | 2 |  |  | Version 1
Change Request Log | 3,4,5 |  |  |  | Version 1 | Updated | Updated
Change Request Form | 3,4 |  |  |  | Version 1 | Updated
IMS | 3,4 |  |  |  | Version 1 | Updated
Lessons Learned Report | 3,5 |  |  |  | Version 1 |  | Updated
Migration Phase IAA Terms and Conditions (Federal Only) | 3 |  |  |  | Version 1
Intent to Exercise Migration Option (Commercial) | 3 |  |  |  | Version 1
Migration Approach, including Technical Strategies | 3 |  |  |  | Version 1
Go/No-Go Criteria for Go-Live Assessment | 3 |  |  |  | Version 1
Readiness Assessment | 3,4 |  |  |  | Version 1 | Updated
Workforce Assessment | 3,4 |  |  |  | Version 1 | Updated
Training Plan | 3,4 |  |  |  | Version 1 | Updated
Requirements Traceability Matrix (RTM) | 3,4 |  |  |  | Version 1 | Updated
Gap Analysis Report | 3 |  |  |  | Version 1
Validated and Updated As-Is Systems Environment | 3 |  |  |  | Version 1
Test Plan | 3,4 |  |  |  | Version 1 | Updated
Configuration Management Plan | 3 |  |  |  | Version 1
CooP and Disaster Recovery Plan | 3 |  |  |  | Version 1
Interface Strategy | 3 |  |  |  | Version 1
Enhancement Strategy | 3 |  |  |  | Version 1
Documented Data Structure and Mapping | 3 |  |  |  | Version 1
Data Conversion Plan | 3,4 |  |  |  | Version 1 | Updated
Contact Center Strategy | 3 |  |  |  | Version 1
Operations & Maintenance (O&M) Service Level Agreements (SLAs) | 3,4 |  |  |  | Version 1 | Updated | Updated
O&M Governance Charter | 4,5 |  |  |  |  | Version 1 | Updated
O&M Contract or IAA | 4 |  |  |  |  | Version 1
Contingency Plan | 4 |  |  |  |  | Version 1
Go/No-Go Readiness Criteria | 4 |  |  |  |  | Version 1
Go/No-Go Assessment Report | 4 |  |  |  |  | Version 1
Target State Organization Design | 4 |  |  |  |  | Version 1
Workforce Transition Strategy | 4 |  |  |  |  | Version 1
Targeted Cutover Communications Plan | 4 |  |  |  |  | Version 1
Training Materials | 4,5 |  |  |  |  | Version 1 | Updated
Training Evaluations | 4 |  |  |  |  | Version 1
Security Documentation, including Security Test Results and ATO | 4 |  |  |  |  | Version 1
Privacy Documentation, including Initial Privacy Assessment, FIPS 199, System of Records Notice (SORN), Privacy Impact Assessment | 4 |  |  |  |  | Version 1
Baselined List of ID Credentials | 4 |  |  |  |  | Version 1
Configuration Workbooks | 4 |  |  |  |  | Version 1
Interface Control Document | 4 |  |  |  |  | Version 1
Reports Design Document | 4 |  |  |  |  | Version 1
Mock Conversion Report | 4 |  |  |  |  | Version 1
Conversion Defect Log | 4 |  |  |  |  | Version 1
Test Scripts | 4 |  |  |  |  | Version 1
Test Results Report | 4 |  |  |  |  | Version 1
Test Defect Log | 4 |  |  |  |  | Version 1
Cutover Plan | 4 |  |  |  |  | Version 1
Target State Process Maps | 4 |  |  |  |  | Version 1
Standard Operating Procedures (SOPs) | 4,5 |  |  |  |  | Version 1 | Updated
Final Report on Success Metrics | 5 | [5 empty] | Version 1
Lessons Learned Questionnaire | 5 | [5 empty] | Version 1
O&M SLA Performance Reports | 5 | [5 empty] | Version 1
Completed Training Evaluations | 5 | [5 empty] | Version 1
O&M Communications and Training Plan | 5 | [5 empty] | Version 1
Communications Materials | 5 | [5 empty] | Version 1
Post Implementation and Evaluation Report | 5 | [5 empty] | Version 1
Decommission Report | 5 | [5 empty] | Version 1
Process Flows | 5 | [5 empty] | Version 1