## Schedule Template
Phase | Task Name | Duration | % Complete | Start | Finish | Actual Start | Actual Finish | Predecessors | Successors | Resource Type
| <<Name of the Migration Project>> |  | 0%
0 | Assessment |  | 0%
| Define Vision |  | 0%
| Develop Major IT Business Case |  | 0%
1 | Readiness |  | 0%
| Establish Initial Customer PMO and Processes |  | 0%
| Establish Customer Governance Structure and Processes |  | 0%
| Establish Customer Risk Processes |  | 0%
| Conduct Procurement Planning |  | 0%
| Develop Life Cycle Cost in the Business Case |  | 0%
| Define Benefits of the Program |  | 0%
| Define Change Management Approach |  | 0%
| Understand As-Is Workforce |  | 0%
| Define As-Is and Initial Target State Systems Environments |  | 0%
| Plan and Conduct Initial Data Quality Assessment |  | 0%
| Develop Initial Target State Concept of Operations and Scope of Services |  | 0%
| Review Standard Business Capabilities & Document Initial Business Capabilities |  | 0%
2 | Selection |  | 0%
| Select Provider for Engagement |  | 0%
| Update Life Cycle Cost Estimate (LCCE) for Engagement, Migration, and O&M |  | 0%
| Monitor and Control Program Exectuion |  | 0%
| Maintain and Execute Risk Processes |  | 0%
| Design Labor Relations Outreach |  | 0%
| Develop Change Management Plan |  | 0%
| Conduct Initial Data Cleansing Activities |  | 0%
| Develop a Decommission Plan |  | 0%
| Understand As-Is Business Processes |  | 0%
3 | Engagement |  | 0%
| Integrate PMO Structures |  | 0%
| Integrate Governance Structures |  | 0%
| Update and Maintain Procurement Plans |  | 0%
| Monitor and Control Program Execution |  | 0%
| Maintain and Execute Risk Processes |  | 0%
| Finalize Migration Approach |  | 0%
| Update LCCE for Migration and O&M |  | 0%
| Engage with Labor Relations |  | 0%
| Execute Change Management |  | 0%
| Develop Training Plan |  | 0%
| Finalize Requirements |  | 0%
| Conduct Requirements Fit-Gap Analysis |  | 0%
| Finalize Target State Systems Environment |  | 0%
| Develop Technical Strategy |  | 0%
| Prepare Data for Mock Conversions (Data Cleansing, Data Mapping) |  | 0%
| Finalize Target State Concept of Operations |  | 0%
| Define Contact Center Structure |  | 0%
| Define Service Level Agreements (SLAs) |  | 0%
4 | Migration |  | 0%
| Monitor and Control Program Execution |  | 0%
| Maintain and Execute Risk Processes |  | 0%
| Develop O&M Governance |  | 0%
| Prepare O&M Scope of Services and Contracts |  | 0%
| Assess Readiness for Go-Live |  | 0%
| Update LCCE for O&M |  | 0%
| Design Target State Organization |  | 0%
| Execute Workforce Transition and Prepare for Go-Live |  | 0%
| Execute Training for Go-Live |  | 0%
| Execute Labor Relations Strategy |  | 0%
| Conduct Security and Privacy Reviews |  | 0%
| Define Roles and User Access |  | 0%
| Configure Systems |  | 0%
| Design and Develop Interfaces |  | 0%
| Design and Develop Reports |  | 0%
| Conduct Mock Conversions |  | 0%
| Test Systems and Processes |  | 0%
| Develop and Execute Cutover Plan for Go-Live |  | 0%
| Finalize SLAs |  | 0%
| Design Target State Processes |  | 0%
5 | Operations |  | 0%
| Review Performance against Expected Benefits |  | 0%
| Collect Lessons Learned |  | 0%
| Implement O&M Governance |  | 0%
| Support Stabilization and Perform Change Management |  | 0%
| Maintain Applications Post Go-Live |  | 0%
| Decommission Legacy Systems |  | 0%
| Conduct Continuous Process Improvement |  | 0%
| Manage Contact Center |  | 0%
| Monitor and Update SLAs |  | 0%